## Sheet1
Project Name | Project Number | Request Number | Requested By | Request Title | Change Description | Change Reason
Secured Lead Process (XER100007 - 002) | (XER100007 002) | 1 | Angus White / Anya Kuenen-Perkins | Flythrough URL Activity Moved in the Workflow | Instead of having the attach flythrough URL activity in the middle of the workflow and being required before the workflow can continue, this activity should now be moved to the end of the workflow with the assumption an Architect may not attach the Flythrough for a few weeks. | It could be weeks before the architect decides to attach these URLs, therefore it shouldn't hold up the rest of the workflow.
Secured Lead Process (XER100007 - 002) | (XER100007 002) | 2 | Angus White / Anya Kuenen-Perkins | Uploading 360 Images to WordPress | An additional request has been made from HOKO for URLs which link to “360 Images” be copied from Monday and pasted to the relevant clients WordPress profile under the “VR” heading. | This is an additional request which was not included in the initial SoW
Sales Order Processing (XER100008 - 001) | (XER100008 - 001) | 7 | Andrew Groat / Angus White | Update Success Log Tables | Add additional fields to show process success | Allow easy readibility for client of where process may have failed
McGo Warranty Extract (XER100007 - 002) | (XER100009 006) | 13 | Jordan Schlansky | Send Data via Api | Use the SNOW API to obtain and send data | Will speed up process and remove steps on the UI Workflow
HOKO - Secured Lead Process (XER100007 - 002) |  |  | Angus White / Anya Kuenen-Perkins | Flythrough URL Activity Moved in the Workflow | Instead of having the attach flythrough URL activity in the middle of the workflow and being required before the workflow can continue, this activity should now be moved to the end of the workflow with the assumption an Architect may not attach the Flythrough for a few weeks. | It could be weeks before the architect decides to attach these URLs, therefore it shouldn't hold up the rest of the workflow.
HOKO - Secured Lead Process (XER100007 - 002) |  |  | Angus White / Anya Kuenen-Perkins | Flythrough URL Activity Moved in the Workflow | Instead of having the attach flythrough URL activity in the middle of the workflow and being required before the workflow can continue, this activity should now be moved to the end of the workflow with the assumption an Architect may not attach the Flythrough for a few weeks. | It could be weeks before the architect decides to attach these URLs, therefore it shouldn't hold up the rest of the workflow.
HOKO - Secured Lead Process (XER100007 - 002) | (XER100007 002) | 1 | Angus White / Anya Kuenen-Perkins | Flythrough URL Activity Moved in the Workflow | Instead of having the attach flythrough URL activity in the middle of the workflow and being required before the workflow can continue, this activity should now be moved to the end of the workflow with the assumption an Architect may not attach the Flythrough for a few weeks. | It could be weeks before the architect decides to attach these URLs, therefore it shouldn't hold up the rest of the workflow.
HOKO - Secured Lead Process (XER100007 - 002) | (XER100007 002) | 1 | Angus White / Anya Kuenen-Perkins | Flythrough URL Activity Moved in the Workflow | Instead of having the attach flythrough URL activity in the middle of the workflow and being required before the workflow can continue, this activity should now be moved to the end of the workflow with the assumption an Architect may not attach the Flythrough for a few weeks. | It could be weeks before the architect decides to attach these URLs, therefore it shouldn't hold up the rest of the workflow.